## Sheet1
ID | Built No. | Bug Name | Bug Description | Steps Taken | Seriousness (1-10) | Frequency | Status
1 | 0.01 | Empty account field | Unable to proceed to main menu, program hang | 1. Press enter for all 3 fields in login | 10 | 3 out of 3 | Solved
2 | 0.01 | Incorrect user account | Proceed to main menu when account does not exist, main menu in infinite loop | 1. Enter ID: Adler 2. Enter Password: Adler 3. Enter User Type: Staff | 10 | 3 out of 3 | Solved
3 | 0.03 | Unable to compile | Too many errors | 1. ./make.sh (to compile all the files) | 10 | 3 out of 3 | Solved
4 | 0.04 | Missing WMTTransactionData.txt to read | Unable to proceed to main menu due to missing file | 1. g++ -Wall -Werror -std=c++11 *.cpp | 10 | 3 out of 3 | Solved
5 | 0.06 | Printing summary does not display summary | After selecting print summary result, nothing was being displayed | 1. After login with managerUser 2. Select Option 7 3. Select Option A 4.Pressed enter when prompt to input date and time | 8 | 3 out of 3 | Pending
6 | 0.06 | Rest of the functions are not up yet | No function was done when choice 1-6 is selected in main menu | 1. After login with managerUser 2. Select Option 1-6 | 8 | 3 out of 3 | Pending
7 | 0.08 | Process Transaction Function not working properly with transaction database text file | Text file storing data of stocks and transaction were wiped after executing .exe file | 1. After login with staff User ID & PASSWORD 2. Type in item ID | 10 | 3 out of 3 | Pending